## MARKETING CHECKLIST
RESTAURANT MARKETING CHECKLIST
Track marketing tasks by category, owner, and deadline. Status, Priority, and Budget cells are editable dropdowns/inputs - overdue tasks highlight automatically.
# | Category | Task | Status | Priority | Due Date | Assigned To | Budget ($) | % Complete | Notes
1 | Website | Launch or update restaurant website with current menu | Completed | High | 2026-05-31 | Web Team | 1500 | 100% | Includes mobile-responsive redesign
2 | Website | Add online reservation / waitlist widget | In Progress | High | 2026-07-05 | Web Team | 400 | 50% | Integrate with OpenTable or Resy
3 | Website | Set up online ordering / delivery integration | Not Started | High | 2026-07-14 | Web Team | 800 | 0% | Connect to DoorDash, UberEats APIs
4 | Website | Optimize site for local SEO (NAP consistency, schema markup) | In Progress | Medium | 2026-07-10 | Marketing Team | 0 | 50% | Name/Address/Phone must match GMB listing
5 | Website | Add high-quality food photography to menu pages | Not Started | Medium | 2026-07-21 | Marketing Team | 600 | 0% | Schedule photographer for next menu refresh
6 | Social Media | Claim and verify Google Business Profile | Completed | High | 2026-05-16 | Marketing Team | 0 | 100% | Critical for local search visibility
7 | Social Media | Post daily specials on Instagram | In Progress | High | 2026-07-01 | Social Team | 0 | 50% | Use June promo image set
8 | Social Media | Post weekly specials on Facebook | In Progress | Medium | 2026-07-02 | Social Team | 0 | 50% | Cross-post from Instagram
9 | Social Media | Set up TikTok account and post short-form video content | Not Started | Medium | 2026-07-20 | Social Team | 200 | 0% | Behind-the-scenes kitchen content
10 | Social Media | Run monthly Instagram/Facebook giveaway | Not Started | Low | 2026-07-30 | Marketing Team | 150 | 0% | Partner with local supplier for prize
11 | Reviews | Set up review monitoring (Google, Yelp, TripAdvisor) | Completed | High | 2026-05-01 | Marketing Team | 0 | 100% | Use review aggregator tool
12 | Reviews | Respond to all new reviews within 48 hours | In Progress | High | 2026-06-30 | Manager | 0 | 50% | Ongoing task - track weekly
13 | Reviews | Request reviews from satisfied repeat customers | Not Started | Medium | 2026-07-07 | Front of House | 0 | 0% | Add QR code to receipts
14 | Advertising | Run targeted Facebook/Instagram ad campaign | Not Started | High | 2026-07-15 | Marketing Team | 500 | 0% | Target 5-mile radius, lunch crowd
15 | Advertising | Set up Google Ads for local search terms | Not Started | Medium | 2026-07-18 | Marketing Team | 600 | 0% | Target "restaurants near me" queries
16 | Advertising | Print and distribute local flyers / menu inserts | Not Started | Low | 2026-07-25 | Marketing Team | 250 | 0% | Partner with nearby businesses
17 | PR | Pitch local food blogger / journalist for feature | Not Started | Medium | 2026-07-20 | Owner | 0 | 0% | Offer complimentary tasting menu
18 | PR | Submit restaurant to local "best of" guides | Not Started | Low | 2026-07-28 | Marketing Team | 0 | 0% | Check submission deadlines
19 | Events | Plan grand-reopening / seasonal event | Not Started | High | 2026-08-04 | Owner | 2000 | 0% | Coordinate with PR and social teams
20 | Events | Host weekly trivia or live music night | Not Started | Medium | 2026-07-12 | Manager | 300 | 0% | Recurring weekly draw for slow nights
21 | Print | Update printed menus with new seasonal items | In Progress | Medium | 2026-07-03 | Manager | 300 | 50% | Coordinate with chef on final pricing
22 | Email | Build email list via website signup and in-store QR | In Progress | Medium | 2026-07-08 | Marketing Team | 0 | 50% | Offer 10% off first order incentive
23 | Email | Send monthly newsletter with promotions | Not Started | Medium | 2026-07-15 | Marketing Team | 100 | 0% | Use Mailchimp or similar platform
SUMMARY
Total Tasks |  | 23
Completed |  | 3
In Progress |  | 7
Not Started |  | 13
Overdue (Not Completed) |  | 15
Completion % |  | 28.26%
Total Budget Allocated |  | 7700

## DASHBOARD
MARKETING CHECKLIST - DASHBOARD
Auto-calculated from the Marketing Checklist sheet. Add or update tasks there and this dashboard refreshes automatically.
KEY PERFORMANCE INDICATORS
23 |  | 28.26% | 15 | 6 |  | 7700
TOTAL TASKS |  | COMPLETION RATE | OVERDUE TASKS | HIGH PRIORITY OPEN |  | TOTAL BUDGET ALLOCATED
TASKS BY STATUS |  |  | OPEN TASKS BY CATEGORY
Not Started |  | 13 | Category | Open Tasks | Budget ($)
In Progress |  | 7 | Website | 4 | 3300
Completed |  | 3 | Social Media | 4 | 350
On Hold |  | 0 | Reviews | 2 | 0
|  |  | Advertising | 3 | 1350
|  |  | PR | 2 | 0
|  |  | Events | 2 | 2300
|  |  | Print | 1 | 300
|  |  | Email | 2 | 100

## CALENDAR VIEW
MARKETING CHECKLIST - CALENDAR / TIMELINE VIEW
Tasks sorted chronologically by due date for at-a-glance planning. This view pulls directly from the Marketing Checklist sheet.
Due Date | Days Until Due | Category | Task | Status | Assigned To
2026-05-01 | -81 | Reviews | Set up review monitoring (Google, Yelp, TripAdvisor) | Completed | Marketing Team
2026-05-16 | -66 | Social Media | Claim and verify Google Business Profile | Completed | Marketing Team
2026-05-31 | -51 | Website | Launch or update restaurant website with current menu | Completed | Web Team
2026-06-30 | -21 | Reviews | Respond to all new reviews within 48 hours | In Progress | Manager
2026-07-01 | -20 | Social Media | Post daily specials on Instagram | In Progress | Social Team
2026-07-02 | -19 | Social Media | Post weekly specials on Facebook | In Progress | Social Team
2026-07-03 | -18 | Print | Update printed menus with new seasonal items | In Progress | Manager
2026-07-05 | -16 | Website | Add online reservation / waitlist widget | In Progress | Web Team
2026-07-07 | -14 | Reviews | Request reviews from satisfied repeat customers | Not Started | Front of House
2026-07-08 | -13 | Email | Build email list via website signup and in-store QR | In Progress | Marketing Team
2026-07-10 | -11 | Website | Optimize site for local SEO (NAP consistency, schema markup) | In Progress | Marketing Team
2026-07-12 | -9 | Events | Host weekly trivia or live music night | Not Started | Manager
2026-07-14 | -7 | Website | Set up online ordering / delivery integration | Not Started | Web Team
2026-07-15 | -6 | Advertising | Run targeted Facebook/Instagram ad campaign | Not Started | Marketing Team
2026-07-15 | -6 | Email | Send monthly newsletter with promotions | Not Started | Marketing Team
2026-07-18 | -3 | Advertising | Set up Google Ads for local search terms | Not Started | Marketing Team
2026-07-20 | -1 | Social Media | Set up TikTok account and post short-form video content | Not Started | Social Team
2026-07-20 | -1 | PR | Pitch local food blogger / journalist for feature | Not Started | Owner
2026-07-21 | 0 | Website | Add high-quality food photography to menu pages | Not Started | Marketing Team
2026-07-25 | 4 | Advertising | Print and distribute local flyers / menu inserts | Not Started | Marketing Team
2026-07-28 | 7 | PR | Submit restaurant to local "best of" guides | Not Started | Marketing Team
2026-07-30 | 9 | Social Media | Run monthly Instagram/Facebook giveaway | Not Started | Marketing Team
2026-08-04 | 14 | Events | Plan grand-reopening / seasonal event | Not Started | Owner
Formulas:
Days Until Due = [Due Date]-TODAY()

## COMPACT LAYOUT
MARKETING CHECKLIST - COMPACT LAYOUT
Minimalist 4-column view (Category, Task, Status, Notes) for quick on-the-spot checks or printed staff handouts. Pulls live from Marketing Checklist.
# | Category | Task | Status | Notes
1 | Website | Launch or update restaurant website with current menu | Completed | Includes mobile-responsive redesign | 99999
2 | Website | Add online reservation / waitlist widget | In Progress | Integrate with OpenTable or Resy | 2026-07-05
3 | Website | Set up online ordering / delivery integration | Not Started | Connect to DoorDash, UberEats APIs | 2026-07-14
4 | Website | Optimize site for local SEO (NAP consistency, schema markup) | In Progress | Name/Address/Phone must match GMB listing | 2026-07-10
5 | Website | Add high-quality food photography to menu pages | Not Started | Schedule photographer for next menu refresh | 2026-07-21
6 | Social Media | Claim and verify Google Business Profile | Completed | Critical for local search visibility | 99999
7 | Social Media | Post daily specials on Instagram | In Progress | Use June promo image set | 2026-07-01
8 | Social Media | Post weekly specials on Facebook | In Progress | Cross-post from Instagram | 2026-07-02
9 | Social Media | Set up TikTok account and post short-form video content | Not Started | Behind-the-scenes kitchen content | 2026-07-20
10 | Social Media | Run monthly Instagram/Facebook giveaway | Not Started | Partner with local supplier for prize | 2026-07-30
11 | Reviews | Set up review monitoring (Google, Yelp, TripAdvisor) | Completed | Use review aggregator tool | 99999
12 | Reviews | Respond to all new reviews within 48 hours | In Progress | Ongoing task - track weekly | 2026-06-30
13 | Reviews | Request reviews from satisfied repeat customers | Not Started | Add QR code to receipts | 2026-07-07
14 | Advertising | Run targeted Facebook/Instagram ad campaign | Not Started | Target 5-mile radius, lunch crowd | 2026-07-15
15 | Advertising | Set up Google Ads for local search terms | Not Started | Target "restaurants near me" queries | 2026-07-18
16 | Advertising | Print and distribute local flyers / menu inserts | Not Started | Partner with nearby businesses | 2026-07-25
17 | PR | Pitch local food blogger / journalist for feature | Not Started | Offer complimentary tasting menu | 2026-07-20
18 | PR | Submit restaurant to local "best of" guides | Not Started | Check submission deadlines | 2026-07-28
19 | Events | Plan grand-reopening / seasonal event | Not Started | Coordinate with PR and social teams | 2026-08-04
20 | Events | Host weekly trivia or live music night | Not Started | Recurring weekly draw for slow nights | 2026-07-12
21 | Print | Update printed menus with new seasonal items | In Progress | Coordinate with chef on final pricing | 2026-07-03
22 | Email | Build email list via website signup and in-store QR | In Progress | Offer 10% off first order incentive | 2026-07-08
23 | Email | Send monthly newsletter with promotions | Not Started | Use Mailchimp or similar platform | 2026-07-15
NEXT UPCOMING TASK (NOT YET COMPLETED)
Respond to all new reviews within 48 hours
Nearest due date (helper): | 2026-06-30

## SEO & LISTING
SEO & WEBSITE LISTING - MARKETING CHECKLIST
Copy-paste ready content for the resources/templates download page. Reference content, not part of the working checklist.
FILE NAMING
Recommended filename | restaurant-marketing-checklist.xlsx
Alt formats to offer | Google Sheets (.gsheet link) and CSV export
PAGE METADATA
Page Title | Restaurant Marketing Checklist Template (Excel / Google Sheets)
Meta Keywords | restaurant marketing plan, marketing checklist, social media checklist, email marketing template, restaurant promotions, free restaurant template
Meta Description | Free Excel/Google Sheets marketing checklist for restaurants. Includes website, social media, advertising & promotions tasks with status tracking. Editable categories and due dates.
DOWNLOAD PAGE - DESCRIPTION
Body copy | Optimize your restaurant's marketing with our Restaurant Marketing Checklist template. This Excel/Google Sheets file covers essential tasks - from building your website and setting up social media, to managing reviews and local ads. Track progress with drop-down status fields and due dates.
DOWNLOAD PAGE - FEATURES (bullet list)
Feature 1 | Organized by marketing categories (Website, Social Media, Reviews, Advertising, PR, Events, Print, Email)
Feature 2 | Status dropdowns and conditional highlights for overdue and due-soon tasks
Feature 3 | Includes 23 pre-filled sample tasks for a quick start (e.g. "Claim Google Business Profile")
Feature 4 | Auto-calculated completion %, budget totals, and a visual KPI dashboard
Feature 5 | Compact and Detailed layout views, plus a chronological Calendar View
Feature 6 | Printable checklist (landscape) and mobile/tablet-friendly design
DOWNLOAD PAGE - INSTRUCTIONS
Step 1 | Download the Excel or Google Sheets file
Step 2 | Customize categories and tasks as needed for your restaurant
Step 3 | List your marketing actions with deadlines and assign an owner
Step 4 | Update status as you work - overdue and due-soon tasks highlight automatically
Step 5 | Review the Dashboard weekly; export or print to share with your team
LICENSE
License type | Free for personal and commercial use (Creative Commons BY)
Attribution requirement | Please credit RestaurantAssociation.com if republishing or redistributing this template
SOURCES / CITATIONS (for page footer)
Reference basis | Based on restaurant industry marketing best practices and templates, including guidance referenced from Coastapp's restaurant marketing checklist and related industry resources on social media, reviews, and local advertising for restaurants
COMPANION TEMPLATE NOTE
Cross-reference | This is the Marketing Checklist companion to the Restaurant Health Inspection Checklist workbook - both follow the same SEO and listing format for consistency across the Resources/Templates page
MARKETING TASK WORKFLOW (PROCESS OUTLINE)
1. Identify marketing task and assign it to a category (Website, Social, Reviews, Advertising, PR, Events, Print, Email)
2. Set Priority, Due Date, and Assigned To
3. Mark Status as work begins (Not Started → In Progress)
4. Track budget if applicable; update Notes with relevant links or context
5. Mark Completed once finished and verified
6. Review Dashboard weekly to catch overdue or high-priority open items
7. Use Calendar View to plan the upcoming week/month of marketing activity

## INSTRUCTIONS
RESTAURANT MARKETING CHECKLIST - GUIDE
HOW TO USE THIS WORKBOOK
• 1. MARKETING CHECKLIST - the main task list, organized by category (Website, Social Media, Reviews, Advertising, PR, Events, Print, Email). Update Status, Priority, Due Date, Assigned To, and Budget as you work.
• 2. DASHBOARD - auto-calculated KPIs (completion rate, overdue tasks, high-priority open items, total budget) plus a status breakdown chart and per-category open-task/budget table.
• 3. CALENDAR VIEW - the same tasks sorted chronologically by due date, for at-a-glance weekly/monthly planning.
• 4. Add new rows directly to the Marketing Checklist sheet as new campaigns arise; Dashboard and Calendar View formulas reference fixed ranges, so extend the range if you add many new rows (see Customizing section below).
STATUS & PRIORITY DEFINITIONS
• Not Started - task identified but no work has begun.
• In Progress - actively being worked on.
• Completed - finished and verified.
• On Hold - paused, awaiting budget, approval, or external dependency.
• Priority (High/Medium/Low) - used to triage attention; High-priority open tasks surface separately on the Dashboard.
CONDITIONAL FORMATTING LOGIC
• Overdue (red): Due Date is before today AND Status is not "Completed".
• Due soon (amber): Due Date falls within the next 3 days AND Status is not "Completed".
• Completed (green): Status = "Completed".
• Not started (gray): Status = "Not Started".
• High priority (red text): Priority = "High" - draws attention regardless of due date.
FORMULAS USED
• % Complete (per row): 100% if Completed, 50% if In Progress, 25% if On Hold, 0% if Not Started.
• Completion Rate (Dashboard): Average of all row % Complete values.
• Overdue Tasks: Counts rows where Due Date < TODAY() and Status ≠ Completed.
• Total Budget Allocated: Sum of the Budget column.
• Category Open Tasks / Budget: COUNTIFS / SUMIF filtered by category and status.
PRINTABLE LAYOUT
• Marketing Checklist and Calendar View sheets are designed for landscape printing - use File > Print, set orientation to Landscape, and "Fit to 1 page wide".
• Freeze header rows are already applied so headers repeat as you scroll/print across pages.
MOBILE & GOOGLE SHEETS USE
• All dropdowns, conditional formatting, and formulas carry over to Google Sheets.
• No macros are used (per best practice for cross-platform compatibility) - all automation is formula-based.
• On mobile, consider hiding the Notes column (right-click > Hide Column) for a more compact view.
CUSTOMIZING THIS TEMPLATE
• Add new tasks: insert rows within the Marketing Checklist table (between existing data rows) so formatting and dropdowns carry through automatically.
• Add new categories: update the Category dropdown list (Data > Data Validation on column C) and add corresponding rows to the Dashboard's category breakdown table.
• Extend formula ranges: if you add many new tasks beyond the current range, update the cell ranges referenced in Dashboard and Calendar View formulas to include the new rows.
• Rename / add Assigned To options via the dropdown on column H.
EXPORT OPTIONS
• PDF: File > Print > Save as PDF, preserving landscape layout and color highlighting.
• CSV: File > Save As > CSV for import into project management tools (note: formulas, dropdowns, and formatting will be lost in CSV).